## Sheet1
| 2019-10-05 | 2019-10-10 | 2019-10-15 | 2019-10-20 | 2019-10-25 | 2019-10-30 | 2019-11-05 | 2019-11-10 | 2019-11-15 | 2019-11-20 | 2019-11-25 | 2019-11-30 | 2019-12-05 | 2019-12-10 | 2019-12-15 | 2019-12-20 | 2019-12-25 | 2019-12-30 | 2019-01-05 | 2019-01-10 | 2019-01-15 | 2019-01-20 | 2019-01-25 | 2019-01-30 | 2019-02-05 | 2019-02-10 | 2019-02-15 | 2019-02-20 | 2019-02-25 | 2019-02-28 | 2019-03-05 | 2019-03-10 | 2019-03-15 | 2019-03-20 | 2019-03-25 | 2019-03-30 | 2019-04-05
1 User Interface
1.1 Basic Wireframe
1.2 Low-Fidelity Design
1.3 Basic Sprites
1.4 Mock Interface
2 Initial Pseudocode
2.1 Level Generation (enemies/puzzles)
2.2 Health and Points
2.3 Weapons and Customisation
3 Database Design
3.1 Database of Enemies
3.2 Database of Levels
3.3 Database of Weapons
4 Implementation
4.1 Level Generation (enemies/puzzles)
4.2 Health and Points
4.3 Weapons and Customisation
4.4 Database of Enemies
4.5 Database of Levels
4.6 Database of Weapons
4.7 Sprites
5 Testing
5.1 Playing Through the Game
5.2 Fix Issues
5.3 Other People Play the Game
5.4 Fix Issues
5.5 Final Test
6 Final Documentation
6.1 Place All Documentation In Order
6.2 Print Documentation